## 2018
Project Type | Project Task | Status | Responsible Party | Project Manager | Vendor | Notes | RFQ Status | Quote / Cost | WO # PO | WO Approval Date | Date Completed
Security & Surveillance | Security Camera Upgrades | Completed | RR HOA | Ted Bertele | SSS Camera | SSS Camera will be upgrading the three dome units and the DVR with better resolution units and a more user friendly interface (as soon as we get internet on site). Training for those interested will be available on-site during the installation scheduled for 10/4/17 (Wednesday afternoon). Burt Dibble will be there supervising the install and participating in the user training. | 2017-06-06 | 3700 | 20170831 | 2017-09-05 | 10/4/17 Install 11/10/2017 Internet Repaired & system running
| Gate Repairs | Completed | RR HOA | Ted Bertele | CO Premier Gate | CO Premier Gate will be repairing the loops that were damaged while BDE does the concrete work. They will be installing four loops in the concrete. This will allow us to go back to a secured entrance. We will also be adding the capability to add more remotes by upgrading this interface. These are new remotes and available for $40 each, the old ones will not be compatible. We have five immediately available for sale. Additional units can be purchased from CO Premier or through the HOA. | 2017-04-20 | 6720 | 20170830 | 2017-09-05 | 2017-10-17
| Security Camera Repairs | In progress | RR HOA | Ted Bertele |  | Cable for access island is severed, no connection to DVR. Need to retrench and lay new cable. Talked with Josh at SSSS… Recommended a shallow trench and use a trenchable cable. Camera at keypad is blurry, clean lens or replace camera. Plan on fixing cable in the spring when RR HOA starts with beautification efforts at the front gate. I have CAT5 ethernet and COAX cables, need connector ends.
| Gate System Code Programming and additional remotes | In progress | RR HOA | Ted Bertele | Door King / DGO / CO Premier | Able to access Gate controls using Door King Account Manager Software, updated gate codes per resident requests. Remotes, Door King 890/893/895MAX or eqv. $30 on Amazon
| Remote Cameras | In progress | RR HOA | Ted Bertele | Stealth Cam / Amazon.com | Recommend putting up a few cameras and monitoring access points (San Juan Heights and others) Bushnel - Essential E3 16MP and 20MP (poor amazon reviews) Stealth Cam - G42NG - ordered kit from Amazon | n/a | 171 |  | 2017-09-06 | Camera recovery and analysis 12/2/17
| Bypass Road Security Gate | In progress | RR HOA | Ted Bertele | TBD | There are two locations where trees would support the hanging of a 16 ft gate. Need to review with HOA and make a determination.
| Gate System Upgrades | On Hold | RR HOA | Ted Bertele | CO Premier Gate | Evaluating options for further improvements. Replacing chaotic operating system with better OS. Not sure its necessary, but phone system access will no longer be available in the near future (upgrade required)
| Signage | unknown | RR HOA | Ted Bertele |  | Off the shelf signs for common points of entry to RR explaining: we have cameras, it is a criminal offense in CO to go through a gate onto private property. Maybe a liability sign as well. Previous discussions suggest John Kennedy has them and put them up. Requires followup